## Slide 1: AVTR Bogie 2.0
Dt 30.09.2022

## Slide 2
Contents
Bogie 2.0 – (Rear suspension/ Rear axle)
  Proposal details
3. Time line and Budget estimate

## Slide 3
Existing Vs Proposed
Single casting for two Bogie bkts integrated with X-member.
Metal spring seat on axle.
Separate Bogie bkts with fabricated X-member.
Rubber Bolster on axle with ARB.
Existing
Proposed

## Slide 4
Leaf Spring
Metal wear pad
Spring seat
Axle
Leaf Spring
(First leaf)
Rubber bolster
(Layer of metal plates covered with Rubber)
Axle
Metal spring seat
Rubber Bolster
Wear Pad vs Rubber Bolster

## Slide 5
Rear ARB
Discrete part list:
1. ARB (only length change from BS4)
2. Frame bkt
3. Axle bkt(Integrated for SR/Bolton for HR)
4. Link rod (only length change BS4)
5. Bottom cup
Frame bkt (casting)
Axle bkt (casting)
Link rod (plate)
Bottom cup (casting)
Split bush
Silent bloc bush
Anti Roll Bar (ARB)
SHOULD cost based on weight and front ARB- Rs 12,000/-
Total assy weight – 69 kg (SR)/ 75 kg (HR)
ARB mtg provision is already available in HR axle housing and to be incorporated in Single reduction axle

## Slide 6
Contents
Bogie 2.0 – (Rear suspension/ Rear axle)
  Proposal details
3. Time line and Budget estimate

## Slide 7: Rear axle proposal – Bogie 2.0
All dimensions are in mm
RA1
RA2
Existing
Proposed
Existing
Proposed

## Slide 8: Existing BS6 vs Bogie 2.0 – Brackets
Existing – BS6
V rod Bracket (Bolted)
Middle Block
Ubolt M20
Bottom Clamp
Top Pad - Welded
Proposed – Bogie 2.0
V Rod Bracket - Welded
Middle Block
Spl Bolt – M20x2.5
Bottom Clamp
Wing Brackets - bolted

## Slide 9: Total weight saving in Bogie 2.0 at vehicle level
 | Existing Bogie (Without ARB) | Bogie 2.0 (With ARB) | Difference | Saving at vehicle level
Rear suspension and brackets | SR axle- 1249 HR axle- 1287 | SR axle- 1149 HR axle- 1155 | SR axle-100 HR axle-132 | 184 (SR)
Rear axle and brackets | SR axle - 250 | SR axle – 166 | SR axle - 84 | 
Weight saving:-
Value in Kg
Indicative cost saving is
INR 29,931/-

## Slide 10
Contents
Axle housing strain measurement summary
  Existing BS6 Bogie
  BS6 Bogie with lower spring stiffness
  BS6 Bogie with Rubber Bolster
  BS4 Bogie
Bogie 2.0 – (Rear suspension/ Rear axle)
  Proposal details
  Weight and cost details
3. Time line and Budget estimate

## Slide 11
Time plan
S1 – 16th Nov’22
S2 (CBN release) – 10th Mar’23
S3 (CBN release) – 19th May’23
Month | Aug'22 |  |  |  |  | Sept'22 |  |  |  | Oct'22 |  |  |  |  | Nov'22 |  |  |  | Dec'22 |  |  |  | Jan'23 |  |  |  |  | Feb'23 |  |  |  | Mar'23 |  |  |  | Apr'23 |  |  |  | May'23 |  |  |  |  | Jun'23 |  | Jul'23 | 
Week number | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 31
Phase 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Concept design for rear suspension |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Concept design for rear axle |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Budget approval |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Phase 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Detailed design and CAE - Rear suspension |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Detailed design and CAE - Rear axle |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stage 1 - Rear suspension |  |  |  |  |  |  |  |  |  |  | S1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stage 1 - Rear axle |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | S1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Phase 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Parts development - Rear suspension |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Parts development - Rear axle |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
In house testing - 6P Trials with Rubber Bolster in existing Bogie |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
In house testing - 6P Trials with Final Bogie and Rubber Bolster |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Supplier/ CTL tests -Rear axle |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
In house testing - Strain measurement for Bogie bracket in Pave and Customer sites |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stage 2 - Rear suspension |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | S2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stage 2 – Rear axle |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | S2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stage 2 - CBN release |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | S2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Phase 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Plant fitment trials and sign off |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Field trials in worst case Tipper applications (HR vehicle field conversion) – 2000 hrs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Field trials in worst case Tipper applications (Plant built SR vehicles) – 2000 hrs (Rear suspension) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stage 3 release - Rear suspension |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | S3 |  |  |  |  |  |  |  |  |  | 
Stage 3 release – Rear axle (600 Hrs validation) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | S3 |  |  |  |  |  | 
Stage 3 release – CBN release |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | S3 |  |  |  |  |  | 

## Slide 12
Investment Estimate
Inputs for estimate:-
1 vehicle for 8P validation
1 vehicle for performance test
No separate vehicle planned for Homologation
4 HR vehicle conversion in Field for trials
4 SR vehicle built at Plant for field trials
2 set of vehicle spares for testing
PD
Proto cost (2 vehicles) : 60 L
Parts and spares : 90 L
Performance and component test : 25 L
Homologation cost : 15 L
Development
Development estimate – INR 422.45 L
Notes:-
Scope – Axle brackets are in Meritor scope
Tooling Cost for brake and axle brackets to be validated with Sourcing/ Suppliers
Axle brackets for 18TG SR variants can be made with additional m/c in 16TG Brackets – If tooling decided, budget required shall be INR 52L/-
PD investment estimate – INR 197 L
Total estimate
619.45 L
Rubber bolster : 13.45 L (Proto)/ 89 L (Production) Bogie bracket : 20 L (Proto)/ 50 L (Production) Trunnion : 10 L ARB brkt : 5 L Bogie 2.0 cross member : 15 L (Proto)/ 55L (Production) V Rod bracket (RA1/RA2) : 20 L (Part tooling cost) SBA wing brackets : 4 L (Part tooling cost) Middle block/ spring seat : 8 L (Part tooling cost)- 24 Bottom clamp (LH/RH) : 24 L (Part tooling cost) Mounting bolt : 5 L (Part tooling cost) Integral brake : 25 L Integral brake – Torque plate : 25 L | Additional part tooling cost for HR axle V rod : 10 L V Rod bracket : 20 L Bottom clamp : 24 L
438.45
635.45

## Slide 13
Thank you